## 2022 SLEITI Work plan
| [Sierra Leone] [2022] EITI Work plan | [8 empty] | Deliverable status categories (can be modified) |  | Complete
On track for delivery by agreed timeline
| Approved : [24th March 2022] | [10 empty] | Medium risk - not on track for delivery
High risk - not on track for delivery
Last updated: [24th March 2022]
Monitoring
Objective (Ultimate Outcome) | Rationale: Governance challenges and links to national priorities | Activity No. | Activities | Output | Outcomes (Immediate and Intermediate) | Responsible party | Timeline | Cost (US$) | Funding source |  | Key deliverable | Status | Status details/Description | Comments from stakeholders (describe who) | Adjustments to work plan and implementation
|  | 1 | MSG Governance
Increased citizen's participation and public disclosure through community outreach | Improved collaboraboration and networking among the three constituencies ( Government , companies,CSOs) | 1.1 | Quarterly MSG Meeting | Improved MSG participation and coordination. | Strengthens EITI implementation | SLEITI/MSG | 03/22 - 12/22 | 3000 | GoSL/donor partners |  | Minutes of meetings |  | Ongoing - MSG meetings were held on 10th & 24th March 2022
|  | 1.2 | Collect Current MSG Constituent Information to ensure efficient collaboration |  |  |  |  | 0 |  |  | MSG Database |  | Not started
|  | 1.3 | Develop and print MSG Operations Handbook |  |  |  |  | 5000 |  |  | Training Manual |  | Not started
|  | 1.4 | Peer review visits among the constituents |  |  |  |  | 0
|  | 1.5 | Capacity building |  |  |  |  | 10000
|  | 1.6 | Staff appraisal |  |  |  |  | 0
|  | 1.7 | Design MSG annual Survey for Feedback |  |  |  |  | 5000
|  | 2 | SLEITI Internal/External Capacity Building
| Effective and Efficient secretariat, Development of human capital | 2.1 | Assessment on NS On-line Training on Leadership/Organizational Management/Software | Improved Capacity of SLEITI Secretariat and MSG | Enhanced efficiency and productivity | SLEITI/MSG | 03/22 - 12/22 | 10000 | GoSL/partners |  | Workshop/Training Report |  | Not started
|  | 2.2 | NS-Fundraising and Proposal Writing |  |  |  |  | 1750 |  |  |  |  | Not started
|  | 2.3 | MSG-NS Training: Beneficial Ownership (BO) |  |  |  |  | 0 |  |  |  |  | Not started
|  | 2.4 | Train staff on UN guiding principles on Business and Human Right |  |  |  |  | 1500 |  |  |  |  | Not started
|  | 2.5 | MSG-NS Training: Mainstreaming EITI Data |  |  |  |  | 0 |  |  |  |  | Not started
|  | 3 | Gender Mainstreaming
| Increased inclusivity and protection of women | 3.1 | Organise meeting with the Ministry of Gender & Children Affairs (MGCA) and other stakeholders on gender related information in accordance with the EITI Requirement | Gender Mainstreaming and empowerment | Promote inclusiveness & gender equality | SLEITI/MSG | 05/22 - 08/22 | 744 | GoSL |  | Report |  | Not started
|  | 3.2 | Advocate for gender mainstreaming in MDAs and legislation of the gender Bill. |  |  |  |  | 0 |  |  | Enactment of the Gender Bill
|  | 3.3 | Facilitate the formation of women champion groups in mining and extractive activities |  |  |  |  | 6000 |  |  | Increase in women's employment in the sector |  | Not started
|  | 3.4 | Raise awareness around women participation in the extractives labour force. |  |  |  |  | 4000 |  |  |  |  | Not started
|  | 4 | Environmental Engagement
| To help promote, protect and preserve the impact of climate change and the extractives on the environment | 4.1 | Coordination meetings with relevant stakeholders in the environment and extractives | Availability of contextual information on the environment | Improved disclosure on environmental impact | SLEITI/ MSG/EPA/CSO | 06/22 - 12/22 | 0 | GoSL |  | Enhanced EITI Report on environmental Impact |  | Not started
|  | 4.2 | Conduct research and monitoring to produce and popularize reports through town hall meeings,road shows,debates etc |  |  |  |  | 25000 | GoSL/Partners |  |  |  | Not started
|  | 4.3 | Advocate for review of policy, regulations and laws on environment, climate change and green energy |  |  |  |  | 0 | GoSL |  |  |  | Not started
|  | 5 | SLEITI Validation
| To ensure all 2018 validation corrective measures are addressed; increase awareness raising through media activities and to ensure preparedness for assessment on the 2019 standard | 5.1 | Hold two-day Pre-Validation Technical mapping and self –assessment workshop for Validation: a) Familiarize with the Validation Templates , b) update progress made in addressing 2018 corrective actions | Assessment of SLEITI Commitment to meeting EITI Requirements | Enhanced preparedness for Validation | SLEITI/MSG | 01/22 - 03/22 | 9580 | GoSL/ACEP/GIZ |  | Workshop Report |  | Completed - This was held in Bo city on 1st - 2nd Feb. 2022
|  | 5.2 | Convene a technical team to support SLEITI MSG complete Validation templates - Stakeholder engagement, Transparency, Outcomes and impact. |  |  |  | 02/22 - 03/22 | 6450 | GoSL/UNDP |  | Completed Validation templates |  | Completed - This was held in York village from 21st -25th Feb. 2022
|  | 5.3 | Pre-Validation Self-Assessment workshop on Validation templates |  |  |  | 02/22 - 03/22 | 2500 | GoSL |  | Workshop Report |  | Completed - This was held at Lacs Villa on 17th March 2022
|  | 5.4 | Media and public campaign ( Radio,TV) town hall meetings, road shows, sign languages, billboards, jingles etc. |  |  |  | 01/22 - 04/22 | 15000 | GoSL |  | Media Reports |  | Ongoing
|  | 5.5 | Collection and submission of documentation for Validation |  |  |  | 01/22 - 03/22 | 0 | GoSL |  | Completed Validation templates |  | Ongoing
|  | 5.6 | SLEITI to engage BSL and SSL to provide recent data (up to 2021) on ASM production for publication on SLEITI website |  |  | SLEITI/BSL/SSL | 02/22 - 03/22 | 0 | GoSL |  | Publication of ASM data on SLEITI website |  | Completed
|  | 5.7 | SLEITI to engage NMA and MMMR to develop templates for systematic disclosure of subnational transfers (DACDF) |  |  | SLEITI/NMA/MMMR | 02/22 - 03/22 | 0 | GoSL |  | Template developed |  | Ongoing
|  | 5.8 | Press Release on Commencement of Validation |  |  | SLEITI/MSG | 2022-03-01 | 3000 | GoSL |  | Media reports |  | Not started
|  | 5.9 | Review Communication Strategy and Update SLEITI Open data policy |  |  |  |  | 0 | GoSL |  | Updated Communication Strategy and Open Data Policy |  | Completed
|  | 5.1 | In-country Validation meetings with stakeholders |  |  |  |  | 0 | GoSL |  | Report/Minutes of engagement |  | Not started
|  | 5.11 | Exit Press Conference by the EITI Validation Team and SLEITI MSG |  |  |  |  | 3000 | GoSL |  | Media coverage report on SLEITI Validation |  | Not started
|  | 6 | Budget Needs Assessment of operations
| Government total commitment in the allocationof resources in the EITI process in Sierra Leone | 6.1 | Increase allocation on EITI budget in the national budget | Enhancement of SLEITI Implementation | Effective & efficient cordination of EITI work plan activities | SLEITI/MSG | 01/22 - 12/22 | 111315 | GoSL |  | Funding to cover staff salaries and office running cost |  | Ongoing
|  | 6.2 | Review and identify funding Agencies and Donors |  |  |  |  | 0 |  |  | Minutes of meetings
|  | 6.3 | Initiate meetings with potential donors |  |  |  |  | 0
|  | 7 | Reporting
| Strengthened oversight and enhance transparency and accountability | 7.1 | Donor Financial and Progress Report (After Project Implementation) | Tracking & disclosure of funding | Effective management and disclosure of funds | SLEITI/MSG | 01/22 - 12/22 | 0 | GOSL |  | Timely report |  | Ongoing
|  | 7.2 | Quarterly Reports - Office of the Vice President (End of each quarter) | [9 empty] | Ongoing
|  | 7.3 | Quarterly update briefing report to MSG (Narrative & Financial Report) | [9 empty] | Ongoing
|  | 7.4 | Produce summary data template for 2020/2021 report | [9 empty] | Not started
|  | 8 | Dissemination of SLEITI 2019 Report
| Increased public access to the SLEITI Report ; Document feedback and identify gaps | 8.1 | Develop Concept Note for MSG approval | Increased understanding of EITI data & extractive sector | Enhanced citizens knowledge and participation in all aspect of SLEITI implementation. | SLEIT/MSG | 03/22 - 07/22 | 50000 | World Bank |  | Approved Concept Note & Report on dissemination activities |  | Not started - This will be implemented in May 2022 as funding has already been received.
To increase citizen's awareness of EITI through increased diclosure and debate- Requirement 2-7 |  | 8.2 | Nationwide dissemination of 2019 SLEITI Report
|  | 8.3 | Produce dissemination report and share findings with MSG and stakeholders
|  | 9 | Produce 2020/2021 SLEITI Report
|  | 9.1 | Develop ToR for IA to be approved by MSG | Production of Annual EITI Report | Increased disclosure of extractive sector information | SLEIT/MSG/IA | 03/22 - 12/22 | 80000 | World Bank |  | Approved ToR, Scoping, Inception and Final Reports and publication on SLEITI website |  | Ongoing - ToR approved by MSG. Recruitment of IA has commenced.
|  | 9.2 | Advertise & recruit IA
|  | 9.3 | MSG approval of Scoping, Inception & final Reports
|  | 9.4 | Publication of the report on SLEITI Website
|  | 9.5 | Produce summary data template for 2020/2021 report
|  | 10 | Dissemination of SLEITI 2020/2021 Report
|  | 10.1 | Develop Concept Note for MSG approval | Increased understanding of EITI data & extractive sector | Enhanced citizens knowledge and participation in all aspect of SLEITI implementation. | SLEIT/MSG | 11/22 - 12/22 | 50000 | World Bank |  | Approved Concept Note & Report on dissemination activities |  | Not started
|  | 10.2 | Nationwide dissemination of 2020/2021 SLEITI Report | [9 empty] | Not started
|  | 10.3 | Produce dissemination report and share findings with MSG and stakeholders | [9 empty] | Not started
|  | 11 | Legal and regulatory reforms
| To create and sustain an investment friendly environment | 11.1 | Review and upadte SLEITI Bill | Improve reforms to strengthen transparency | Passing of SLEITI Bill and other extractive sector Bill | SLEITI/MSG/Parliament/Law Officers department | 04/22 - 12/22 | 0 | GoSL |  | SLEITI Act |  | Ongoing
|  | 11.2 | Collaborate with key stakeholders and institutions including Parliament to legislate the SLEITI Bill into law. |  |  |  |  | 5000 |  |  |  |  | Ongoing
|  | 11.3 | Lobby key stakeholders to develop sector related legislation. |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 11.4 | Engage MDAs to develop policy and plan on contracts disclosure |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 11.5 | Lobby stakeholders to publicly disclose contract & licence awards & transfers ensuring non-trivial deviation from statutory procedures |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 11.6 | Ministry of mines and mineral resources to initiate policy/law on public disclosure of contracts |  |  |  |  | 0 |  |  |  |  | Not started
|  | 11.7 | Strengthen relationship with key integrity institutions (ACC, FIU, ASSL, CAC etc.) |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 12 | Mainstreaming EITI Data
| To meet the objective of Government National Medium Term Development Plan ( MTNDP) which states that by 2023, the Government will “mainstream transparency and accountability practices into the ( Mining) sector, according to the 2016 Extractive Industries Transparency Initiative standards | 12.1 | Map out strategies to implement the recommendations of the feasibility study on mainstreaming EITI data | EITI reporting mainstreamed in government and company operations | Improve timely release of sector related information |  |  | 0 |  |  | Enhanced transparency within the extractive sector |  | Not started
|  | 12.2 | Lobby key stakeholder to systematically disclose All oil, gas and mining licenses and contracts in the area of exploration and production, on a publicly accessible government website/portal in both human and machine-readable formats |  |  |  |  | 3000 | GoSl/Donor |  |  |  | Ongoing
|  | 12.3 | Engage relevant government agencies to commence efforts (for example develops appropriate template or policy/legal provisions) to systematically disclose up-to-date information on their operations (e.g. government revenue data, subnational revenues) in the extractives sector |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 13 | Beneficial Ownership Disclosure
| To maintain the Open Government Partnership's (OGP) goal of bringing government reformers and civil society leaders together to create action plans that make governments more inclusive, responsive, and accountable.The plan offers new commitments on tax, beneficial ownership transparency, and open parliament. Sierra Leone To implement the 2019-2021 Action Plan 2019-2021 which offers commitments on tax, beneficial ownership transparency, and open parliament. | 13.1 | Lobby key stakeholders to enact the Mines & Mineral Development Bill | BO disclosure strengthened | Effective implementation of BO disclosure requirement | SLEITI/MSG/CAC/ACC/FIU/BSL | 03/22 - 12/22 | 0 | GoSL/Donor |  | Improved knowledge of ownership of extractive companies |  | Ongoing
|  | 13.2 | Public Awareness Campaign for BO Sensitization |  |  |  |  | 5000 |  |  |  |  | Ongoing
|  | 13.3 | Map out strategies for implementation of BO study report |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 13.4 | Undertake Study on Phase 2 of BO Implementation |  |  |  |  | 30000 |  |  |  |  | Not started
|  | 13.5 | Work with key agency to support launching of BO registry |  |  |  |  | 0 |  |  |  |  | Not started
|  | 13.6 | Create MoU with key Agency on shared information |  |  |  |  | 1000 |  |  |  |  | Not started
|  | 13.7 | Joint launching of BO Registry, Awareness Raising Event |  |  |  |  | 5000 |  |  |  |  | Not started
|  | 13.8 | BO Technical Working Group Monitor and Evaluate progress and report back to MSG and other key stakeholders on progress |  |  |  |  | 1000 |  |  |  |  | Not started
|  | 14 | Enhanced SLEITI visibility and Impact on EITI Implementation
| To promote transparency in all aspects of the extractive sector | 14.1 | Produce full and summary versions of the 2019 Report | Improved citizens participation in all aspects of SLEITI implementation | Promotes impact of EITI implementation | SLEITI / MSG | 03/22 - 12/22 | 5000 | World Bank, GoSL, ACEP |  | Increased availbility of EITI data and knowledge of the sector. These include Braille version, Minutes of meetings, M&E report on Media analysis |  | Ongoing
|  | 14.2 | Produce 2019 report in Braille format |  |  |  |  | 9200 |  |  |  |  | Completed
|  | 14.3 | Distribute 2019 SLEITI report to Stakeholders (MDAs, CSOs, Media etc.) |  |  |  |  | 500 |  |  |  |  | Ongoing
|  | 14.4 | Undertake Radio and TV Programmes on Findings on 2019 SLEITI report |  |  |  |  | 5000 |  |  |  |  | Ongoing
|  | 14.5 | Publish report findings in newspapers |  |  |  |  | 500 |  |  |  |  | Ongoing
|  | 14.6 | Monitor and Evaluate /Media Analytics |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 14.7 | Hold Public engagement at Key Universities (FBC, NJALA & UNIMAK) |  |  |  |  | 15000 |  |  |  |  | Not started
|  | 14.8 | Hold one press conference in Freetown on the 2019 SLEITI report |  |  |  |  | 1000 |  |  |  |  | Not started
|  | 14.9 | Hold one Capacity building workshop with CSOs and Journalists on the new EITI requirements |  |  |  |  | 12000 |  |  |  |  | Not started
|  | 14.1 | Undertake outreach activities to mining communities on SLEITI process |  |  |  |  | 40000 |  |  |  |  | Not started
|  | 14.11 | Map out strategies to act on the report’s findings and Recommendations |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 14.12 | Link Key achievements and challenges with TV discussions |  |  |  |  | 10000 |  |  |  |  | Not started
|  | 14.13 | Hosting, Upgrade & improve user interface of the SLEITI website |  |  |  |  | 6000 |  |  |  |  | Ongoing
|  | 14.14 | Training on Website maintenance and upkeep |  |  |  |  | 0 |  |  |  |  | Ongoing
|  | 14.15 | Monitoring and Evaluation / Media and Social media Analytics |  |  |  |  | 3000 |  |  |  |  | Ongoing
|  |  | Total |  |  |  |  | 560039