Office of the Vice President

17 Charles Street, Buxton Compound, 2nd Floor,

Freetown, Sierra Leone

Website: www.sleiti.gov.sl

SLEITI SECRETARIAT MONTHLY REPORT

Period Covered: August 2024

Date submitted: 23rd August 2024

SLEITI ACTIVITY REPORT – August 2024

| No. | Activity | Update | Date |
| --- | --- | --- | --- |
| 1 | Local-level Advocacy training on human capital development | SLEITI participated in a three-day advocacy training workshop on human capital development in Koidu City, Kono District, organised by Africa Human Capital Development Plus (HCP+). SLEITI was part of a team that represented the Office of the Vice President. The local-level workshop aimed to empower district-level human capital development advocates and other stakeholders by providing them with the knowledge, skills, and network needed to champion the cause of human capital development at the district/community levels. | Tuesday, 30th July, 2024 |
| 2 | Ministries Cybersecurity Awareness Training | SLEITI attended a one-day cybersecurity awareness training program organised by the National Cybersecurity Coordination Center. The training focused on safeguarding government data and empowering participants to become frontline defenders against cyber threats within the public sector. | Wednesday, 31st July, 2024. |
| 3 | The Committee meet to review the draft SLEITI Bill (Extractive Resources Transparency Bill) and the draft MSG MoU (2024-2027) | Following the MSG meeting on Thursday, 27th June 2024 and discussions around agenda items 4 - Review and signing of SLEITI MSG MoU (2024-2027) and 7 - Update on the draft SLEITI Bill (Extractive Resources Transparency Bill), a committee was formed to review both the draft SLEITI Bill and MoU. The committee met at the SLEITI secretariat’s conference room on Tuesday, 6th August 2024, and reviewed both documents extensively. Inputs and recommendations were incorporated into the documents which will be shared with the MSG for review and approval. | Tuesday, 6th August, 2024. |
| 4 | Implementation catch-up meeting with EITI International Secretariat | The SLEITI secretariat had a virtual meeting with Edwin and Williams from the EITI International Secretariat and extensively discussed the implementation of work plan activities, challenges and priorities for the rest of the year. Other areas discussed were the national coordinators' workshop in Lusaka, Zambia, capacity building workshop for MSG members and the SLEITI secretariat. The meeting was deemed timely and productive. | Thursday, 8th August, 2024. |
| 5 | Audit Service Sierra Leone entrance engagement meeting with Unit under the Office of the Vice President for audit of the financial year to 31st December 2023 | The Secretariat participated in an entrance meeting with Audit Service Sierra Leone to discuss the audit process for the financial year January to December 2023. In the meeting, the Auditors stated that they would commence the audit on Monday, 19th August 2024 and it is expected to last about three weeks. Therefore, all units were requested to get their documents in order as they will be requested at any time during the audit process. | Tuesday, 13th August, 2024. |
| 6 | 2025 Manpower Planning and Budget Hearing | SLEITI was part of a session that met at the Civil Service Training College, Tower Hill, to discuss the 2025 Manpower planning and budget hearing. At the meeting, vacancies for the various units were highlighted including staff members that are due for promotion and training. | Monday, 19th August, 2024. |
| 7 | Meeting with GIZ | SLEITI met with GIZ to discuss the possibility of funding support on key work plan activities that would strengthen EITI implementation in Sierra Leone. Areas of intervention that were discussed included the redevelopment of the SLEITI website, capacity building for MSG members and secretariat staff, and dissemination of the 2022-2023 report. | Wednesday, 21st August, 2024. |