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SLEITI SECRETARIAT MONTHLY REPORT

                               Period Covered: July 2025

                     Date submitted: 8th August 2025

                                 SLEITI KEY ACTIVITY REPORT – JULY 2025

	No.
	Activity
	Update

	1
	Meeting with the Secretary to the Vice President. 
	The National Coordinator (NC) had a productive meeting with the newly appointed Secretary to the Vice President – Mr. Mohamed Brima Dabor. The meeting was crucial for building a collaborative relationship and ensuring the new secretary was well-informed about the EITI process.
The NC provided a detailed report on the status of EITI implementation in Sierra Leone, highlighting progress, challenges, and priorities. 
Mr. Dabor pledged his support to SLEITI and expressed his satisfaction with having a detailed insight into SLEITI’s activities, which he said will help him identify areas for value-add that will enhance the implementation of the EITI Standard.   

	2
	Open Government Partnership (OGP) - Steering Committee Meeting.
	Dr. Sahr Karku - Monitoring and Evaluation Officer, attended the Steering Committee meeting of the Open Government Partnership (OGP) held at the Parliament’s Training Center. He provided an update on SLEITI’s progress in implementing commitments in the National Action Plan Five (NAP 5). His update included the following points:

1. The SLEITI Bill is currently on hold pending Cabinet’s endorsement of the SLEITI Policy.

2. On systematic disclosure, SLEITI is currently engaged with the relevant Ministries, Departments, and Agencies (MDAs) to encourage proactive and routine disclosure of EITI related data.
3. A subcommittee within the newly revitalized Beneficial Ownership (BO) Technical Working Group, headed by the Director General of the Financial Intelligence Agency, has been established to commence work on developing a national BO Regulation.

	3
	Bi–Weekly SLEITI Staff Meeting
	The secretariat held its regular bi-weekly staff meeting, where team members provided comprehensive updates on their activities over the past two weeks. These presentations highlight progress, challenges, and remedial actions. 

This meeting serves as a valuable platform for keeping everyone informed about the overall progress of the work plan implementation. 

	4
	Training on Illicit Financial Flows (IFFs) in the natural resources sector and Resource-Backed Loans (RBLs).  
	The National Coordinator took part in a four-day training workshop from July 8-11, 2025, involving selected senior government officials from several MDAs, as well as members of civil society, relevant local communities, and stakeholders.
The training workshop was organized by the African Development Bank’s (AfDB) Governing Natural Resource Outflows for Enhanced Economic Resilience in Fragile and Transitional Countries in Africa (GONAT), on Illicit Financial Flows (IFFs) in the natural resources sector and Resource-Backed Loans (RBLs).  

The workshop was complemented by a one-day policy dialogue on 11 July 2025, featuring panelists including the Minister of Finance, the Minister of Planning and Economic Development, the Deputy Commissioner of the Anti-Corruption Commission, the Executive Director of Women on Mining and Extractives, the Managing Director of CEMMATS Group, and several other experts. The overarching policy recommendations will be presented for the AfDB as well as to the Government of Sierra Leone for further action. 
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